## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [5 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | WEEKS (Summer Session)(10 weeks) | [11 empty] | WEEKS(Autumn Session)
[18 empty] | (1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | B | B | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Design 3D printer | 1 | 1 | 0 | 0 | 0%
Construct Extrusion System | 2 | 2 | 0 | 0 | 0%
Develop Software for Extrusion System | 3 | 2 | 0 | 0 | 0%
Test Extrusion System | 5 | 1 | 0 | 0 | 0%
Complete Extrusion System | 6 | 2 | 0 | 0 | 0%
Assemble Extrusion System with Industrial Robot | 6 | 2 | 0 | 0 | 0%
Develop Software for Industrial Robot | 7 | 1 | 0 | 0 | 0%
Develop Software for Entire 3D Printing System | 8 | 2 | 0 | 0 | 0%
Test Entire System | 10 | 1 | 0 | 0 | 0%
Complete Prototype of 3D Printer System | 11 | 1 | 0 | 0 | 0%
Test Materials | 11 | 1 | 0 | 0 | 0%
Analyse Performance | 11 | 2 | 0 | 0 | 0%
Make Final Adjustments | 12 | 1 | 0 | 0 | 0%
Draft Thesis | 13 | 9 | 0 | 0 | 0%
Finish all testing and results | 13 | 2 | 0 | 0 | 0%
Study Results | 14 | 1 | 0 | 0 | 0%
Draft Oral Presentation | 21 | 2 | 0 | 0 | 0%
Final Thesis | 22 | 2 | 0 | 0 | 0%